## Defect_tracker
SI No | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status (Open/Closed) | Remarks
1 |  | Dataset contained null email bodies | Milestone 1 | Backend Team | Data Defect | Added null removal & cleaning script |  | Closed | Resolved in preprocessing
2 |  | Special characters not removed from text | Milestone 1 | Backend Team | Logic Defect | Added regex text normalization |  | Closed | Improved accuracy
3 |  | Model misclassifying spam as request | Milestone 2 | Backend Team | Algorithm Defect | Retrained with balanced data |  | Closed | Accuracy improved to 96%
4 |  | API returned 500 for empty input | Milestone 2 | Backend Team | API Defect | Added validation in endpoint |  | Closed | Graceful error added
5 |  | API timeout on large text | Milestone 2 | Backend Team | Performance Defect | Increased timeout & optimization |  | Closed | Stable now
6 |  | Login accepted blank password | Milestone 3 | Frontend Team | Validation Defect | Added required field check |  | Closed | UI validation added
7 |  | Sidebar navigation not switching pages | Milestone 3 | Frontend Team | UI Logic Defect | Corrected session routing |  | Closed | Working properly
8 |  | Category shown as numeric values | Milestone 3 | Frontend Team | Display Defect | Mapped to labels |  | Closed | Shows complaint/request
9 |  | Badges not visible in inbox | Milestone 3 | Frontend Team | UI Defect | Added CSS badge classes |  | Closed | Colors visible
10 |  | Table index started from 0 | Milestone 3 | Frontend Team | Formatting Defect | Changed index +1 |  | Closed | As required
11 |  | Dashboard charts not updating | Milestone 4 | Frontend Team | Integration Defect | Linked session data |  | Closed | Dynamic update
12 |  | EC2 deployment port conflict | Milestone 4 | Backend Team | Deployment Defect | Killed old process |  | Closed | App running
13 |  | Streamlit not found in venv | Milestone 4 | Backend Team | Environment Defect | Activated venv & installed |  | Closed | Fixed
14 |  | API URL hardcoded localhost | Milestone 4 | Frontend Team | Config Defect | Updated to EC2 IP |  | Closed | Live working
15 |  | Script execution indentation error | Milestone 4 | Frontend Team | Syntax Defect | Corrected structure |  | Closed | App stable